## Sheet1
| Challenge | Action | Deliverables | Lead Responsibility
VISION
1 | To develop a shared vision for the ICT sector in line with the NI Economic Strategy and Programme for Government | e-skills UK Employer Board, DETI, Invest NI and DEL will work together to set out a long term vision for the sector for the next five years. | Production of a five year vision for the ICT Sector articulating the likely future demand for jobs, the job types and the relevant skills needs. | e-skills UK, Invest NI, DEL and DETI
THEME 1 – SKILLS PROVISION (RELEVANCE, QUALITY, ETC)
Short term
2 | Understand the demand for ICT Professionals | The e-skills UK Employer Board will continue to use existing labour market information and annually updated forecasting reports to identify specific skills gaps faced by each sub-sector (software development, infrastructure management and applications management) and likely future skills gaps. Consideration may need to be given to making this review process more regular. | Agreement on the specific skills gaps faced by each sub sector. This will include information on the level of experience necessary, the qualification subject and level and numbers required to fill the shortage.
3 |  | The e-skills UK Employer Board will seek support from Invest NI’s Collaborative Network Programme to continue work with the demand side to better understand the range of skills demands in the sector | A more detailed specification of the skills demands of employers in each of the sub sectors
4 | Understand the annual supply of appropriately qualified people relevant to employer need. | Universities and colleges will continue to provide figures regarding predicted outflow from their courses to develop a clear understanding of the provision from our institutions in order to inform actions. | A clear understanding of the numbers of people who can potentially work within the sector.
5 |  | The e-skills UK Employer Board, with the proposed support of their Collaborative Network facilitator, will continue to monitor the dynamics between the sector’s demand for graduates and the numbers supplied through the education and training systems. | A clear understanding of the numbers of graduates who can potentially work in the sector and the requirements of industry.
6 | Address critical skills shortages | The Department for Employment and Learning and Invest NI will continue with the development of existing and pilot provision in software testing.
7 |  | Invest NI will develop a Capital Markets Technology Programme.
8 |  | The Department for Employment and Learning, Invest NI and ICT employers will develop the Academy approach, as used with Software Testers, to address known skills shortages in the software languages, such as Java, C, C+, C#, in applications skills such as Enterprise Application, Applications management and in infrastructure skills such as Unix/Linux, Microsoft and VMWare. | Industry to determine the number of places that should be made available and the specific software language skills required.
9 |  | The IT Professional course, which has been developed by the Department for Employment and Learning and the further education sector, will be validated by the industry, to align the curriculum more closely with the needs of employers. | A refined curriculum for the IT Professional course which ensures that it continues to reflect the current skills needs of local ICT employers.
10 |  | Based on the agreed identified skills gaps the e-skills UK Employer Board will identify the existing relevant provision which meets the agreed skills needs and ways in which uptake can be increased. Support will be sought from Invest NI’s Collaborative Network Programme to appoint a facilitator to assist with this work. | Agreement on the existing provision which meets the skills gaps identified by each sub sector. Ongoing facilitation will be required to monitor and respond to changing needs.
Medium term (30 June 2013)
11 | Encourage the take up for Computer Studies A-Level | The Department of Education, via CCEA, will continue to examine the current provision and range of school computing/ICT qualifications to ensure it meets the needs of ICT courses in universities. | Better alignment of the school computing/ICT qualifications to meet the needs of universities.
12 |  | Ensure Careers teachers in schools and Careers Advisers have access to up to date labour market information to highlight the career opportunities and benefits associated with the ICT Sector to school children and their influencers. | More school students choosing to study Computer Science and Mathematics at A level.
13 |  | The Department of Education will develop and introduce new awareness programmes aimed at encouraging more pupils to choose to study Computer Science. | An increase in the number of students enrolling in Computer Science related subjects.
14 |  | Universities will consider the weighting they give to certain A level courses (such as Computer Studies and Mathematics) through their entry/intake process. | More people entering relevant university courses with appropriate courses at A level.
15 | Incentivise the take up of relevant courses at college and university | Universities will consider the use of bursaries/ scholarships to encourage more people to study Computer Science and Mathematics. | More people entering relevant university courses with appropriate courses at A level.
16 |  | Universities will offer postgraduate MSc courses aimed at non-IT graduates, to meet the demands of the sector. | Appropriate Post Graduate MSc courses at UU and QUB aimed at non-IT graduates in 2012 to deliver approximately 90 qualifications.
17 |  | Industry will support the introduction of a new A level qualification in Software and Systems Development through actions such as provision of ‘guru’ lecturers and through assisting with the continued professional development of teachers, who will deliver the new qualification. | Increased number of teachers capable of delivering the the A level qualification in Software and Systems Development.
18 |  | Further education colleges will offer conversion courses for non-IT graduates. | Appropriate conversion courses for non-IT graduates delivered by further education sector.
19 | Address attrition rates in college and university | Universities and further education colleges will ensure a significant reduction of the high attrition rate from ICT and Computer Science courses. | Continue to implement measures to reduce attrition and monitor progress.
20 | Explore alternative routes into the ICT Sector | The Department of Finance and Personnel and ICT employers, will develop a best practice model to recruit and train apprentices for work within the ICT sector | Government and companies to work together through the the Public/Private ICT Apprenticeship Pilot to develop a best practice model for recruiting and training ICT apprentices to work in the sector
21 |  | The Department for Employment and Learning will explore the possibility of establishing an assistance programme for SMEs to encourage and support them in offering bursaries, scholarships, internships, apprenticeships and/ or placements to students on approved courses. | Increased number of SMEs offering bursaries, scholarships, internships, apprenticeships and/or placements to students on approved courses
THEME 2 SECTOR ATTRACTIVENESS
Short term
22 | Encourage more people to choose the relevant subjects required to work in the sector | Taking into account the previous evaluation of 'Bring IT On', the Department for Employment and Learning, Invest NI and the e-skills UK Employer Board will consider the effectiveness of the communication of key messages to the target audience(s) and their impact. The existing audience will be expanded to include younger children and their influencers. | A reviewed 'Bring IT On' campaign for 2012/13.
|  | The Department for Employment and Learning, Invest NI and the e-skills UK Employer Board will develop a PR campaign to highlight positive aspects of the sector including its recent performance. This will complement the 'Bring IT On' campaign. | An agreed PR strategy for 2012/2013.
Medium term (30 June 2013)
24 | Encourage more people to choose the relevant subjects required to work in the sector | e-skills UK Employer Board will commence the roll out of the revised 'Bring IT On' campaign. | Increased interest and applications to computer/ICT courses (numbers to be defined).
25 |  | e-skills UK Employer Board and the Department for Employment and Learning will implement further direct and indirect campaign activities, in conjunction with the STEM Ambassadors Programme, and upgrade the ‘Bring IT On’ website. | An agreed programme of activities to be taken forward in 2012/2013.
26
27
28 | Encourage those people with the relevant qualifications to work in the sector | The Department for Employment and Learning will, through an attitude survey, investigate the reasons for the high leakage of people from relevant ICT and computer courses. This will build on information already available in the 'Destination of Leavers from Higher Education' survey. | A better understanding of the reasons people choose not to work in the industry so that remedial action to reverse the trend will be identified.
29
30 |  | e-skills UK Employer Board, the Department for Employment and Learning and Invest NI will accelerate the knowledge and experience of key leaders to help address the issue of a shortage of experienced software engineers with management and leadership skills | Increase in the technical and management and leadership skills of key leaders in the sector.
31 | Addressing the gender imbalance within the ICT sector | e-skills UK to continue to deliver Computer Clubs 4 Girls | Increased number of girls choosing to study computer science courses at post-primary level.
THEME 3 – COORDINATION AND COMMUNICATION
Short term
32 | Ensure that there is a coordinated approach to addressing skills shortages within the ICT sector | e-skills UK Employer Board will work with the STEM Business Group to ensure synergy between the actions of the respective groups. | Areas of collaboration agreed.
33 |  | e-skills UK Employer Board and Invest NI will establish an industry led ICT Collaborative Network to gain a better understanding between industry and education science and technology capabilities | Global market opportunities are identified by exploiting the science and technology capabilities in NI.
34 |  | Each Group will develop measures through which more employers will offer meaningful placements. Consideration will be given to the work already being undertaken by the STEM Business sub group in this area. | Increase relevant work placements in scholarships and bursaries in ICT industry.
35 |  | Business members of the ICT Working Group will examine existing best practice (such as the Digital Media and ICT Vendor Alliance Program and Digital Hub) to consider if there are lessons that can be learned. | Agreed actions identified and added into the Action Plan where appropriate.
36 |  | e-skills UK will communicate the availability of alternative provision to encourage individuals into the ICT sector - such as ICT Apprenticeships, Foundation Degrees and Higher National Diplomas (HNDs). | More information available through the careers service and ‘Bring IT On’ website highlighting pathways.
37 |  | e-skills UK Employer Board will ensure key messages regarding the sector are incorporated in the STEM Business sub group's communication plan. | Coordinated approach on STEM.